## Introduction
Planning Your Graduate Research with a Gantt Chart
A graduate degree is a multi-stage project that mixes fixed institutional deadlines (coursework, candidacy, thesis submission windows) with variable research work (design, data collection, analysis, writing). A Gantt chart helps you turn that complexity into a clear plan you can actually follow—and revise—over time. Use this guide alongside your program’s handbook and the Gantt chart template in this document. Add all your tasks and milestones to the Full Program sheet.
How to Think About Your Program Timeline
- Anchor to immovable dates first. Examples: add/drop periods, comprehensive exams windows, ethics/IRB board meeting cycles, funding renewals, thesis submission deadlines, conference deadlines, visa limits, supervisor sabbaticals. - Map the big stages. Typical stages can be: orientation & coursework → proposal → approvals (ethics/permissions) → data gathering → analysis → writing → revisions/defense → submission & archiving. - Plan at two zoom levels: Semester/term level for major gates and deliverables, and Weekly level for execution (reading blocks, lab time, interviews, writing). This chart is divided into weekly blocks to facilitate a more granular approach to your planning. - Expect iteration. Most stages require feedback cycles. Build explicit time for supervisor/committee turnaround and your revisions. - Balance your load. Account for teaching/RA/TA duties, caregiving, illness, and breaks. Sustainable plans finish faster than heroic sprints followed by crashes.
What a Gantt Chart Does for You
A Gantt chart shows tasks as horizontal bars on a timeline. It lets you: - Sequence work and dependencies. (e.g., “Submit ethics” → “Wait for approval” → “Recruit participants”.) - Spot overlaps and bottlenecks. - Reserve time for review cycles. - Track progress and surface risk via status colors or % complete. - Communicate your plan to supervisors and collaborators.
Step-by-Step: Build Your Plan in the Template (with Examples)
1) Collect constraints and deadlines - List non-negotiables in the template’s “Milestones” or top rows. - Examples: “Comprehensive exams window: Sept 15–Oct 15,” “Conference abstract deadline: Feb 1,” “Thesis intake: Aug 1–15.”
2) Break your project into tasks (Work Breakdown) - Aim for tasks 1–3 weeks long so they’re trackable. Include thinking and waiting tasks. - Quant example (survey study): Draft proposal → Supervisor feedback cycle 1 → Revise proposal → Ethics application → Ethics review wait → Pilot survey → Revise instrument → Main data collection → Clean data → Analysis → Draft Results → Draft Discussion → Full draft → Committee feedback → Revise → Defense prep. - Qual example (interviews): Sampling frame → Recruit participants → Conduct 12 interviews → Transcribe → Initial coding → Axial coding → Member checking → Thematic write-up → Draft chapter → Supervisor feedback → Revise. - Humanities example (archival): Identify archives → Request access → Travel logistics → Archive visit 1 → Source cataloging → Theoretical framework memo → Chapter 1 draft → Chapter 2 draft → Advisor feedback → Revise.
3) Estimate durations (be realistic) Use simple methods: - Analogy: How long did similar tasks take you or your lab mates? - Three-point estimate: For each task, note optimistic / most likely / pessimistic (e.g., 1 / 2 / 4 weeks). Plan with the most likely + buffer (see Step 7). - Effort vs. duration: A “10-hour” task may spread over two weeks if you only have 4 focused hours/week.
4) Set dependencies and opportunities to parallelize Common patterns: - Finish-to-start: “Ethics approval” must finish before “Recruit participants.” - Start-to-start: “Literature review (ongoing)” can run alongside “Instrument design.” - Wait states: Represent waiting explicitly (e.g., “Ethics review (waiting)” 4–8 weeks). This prevents phantom free time. - Mini chain (quant example): Proposal (3 wks) → Ethics application (1 wk) → Ethics review (6 wks wait) In parallel during the wait: Advanced Lit Review (4 wks), Pilot coding scripts (2 wks)
5) Place tasks on the calendar - Add non-working periods (exams, holidays, travel). - Add recurring items: “Supervisor meeting” every 2 weeks; “Lab group check-in” monthly.
6) Add milestones - Milestones clarify progress and keep motivation high. - Examples: Proposal approved; Ethics approved; Data collection 50%/100%; First full draft; Committee sign-off; Defense scheduled; Final submission.
7) Add buffers - Task buffers: +20–30% time on research tasks that often expand (analysis, writing, recruitment). - Gate buffers: Add explicit slack before hard deadlines (e.g., finish full draft 4 weeks before submission window).
8) Review weekly; replan monthly - Weekly (15 minutes): Update Done or Not Done; note blockers. - Monthly (30–45 minutes): Shift bars, re-estimate remaining work, and re-baseline if the plan meaningfully changes.
9) Use it as a communication tool - Share the chart before supervisor meetings; highlight decisions needed (e.g., “Need approval to expand sample”). - Export a PDF for committee check-ins and funding reports.

## Full Program
Task ID | Task Name | Category | Duration (weeks) | Preceding Tasks | Custom Start Date | Start Date | End Date |  | Task Done | time axis 2024-08-26 to 2035-12-31
Academic Program Planning Chart
|  | Instructions: 1) Before starting to use this sheet, input your program or project start date below. 2) In the task name column, add your tasks. Each task will automatically get an ID number assigned. 3) Select a category for each task. You can have up to 10 different named categories, the names of which you can edit in the Category Keys section. 4) Assign a duration (in weeks) for each task. 5) If your task has preceding task(s), add them by id number in the preceding tasks column. The chart will automatically assign a beginning and end date for your task based on when the preceding tasks end. 6) You can optionally add a custom start date for your task in the Custom Start Date column. This will override the previous start date calculation. 7) As you complete tasks, remember to change the Task Done cell to Done, to keep better track of your progress. In the other sheets in this document, you can take a more specific look at your project by year. | [5 empty] | Done
Date
|  | Project Start Date: | 2024-09-01
|  |  | Outside Work | Hello |  |  |  | (Do not touch) |  | 2024-08-26: 2024; 2024-12-30: 2024; 2025-01-06: 2025; 2025-12-29: 2025; 2026-01-05: 2026; 2026-12-28: 2026; 2027-01-04: 2027; 2027-12-27: 2027; 2028-01-03: 2028; 2028-12-25: 2028; 2029-01-01: 2029; 2029-12-31: 2029; 2030-01-07: 2030; 2030-12-30: 2030; 2031-01-06: 2031; 2031-12-29: 2031; 2032-01-05: 2032; 2032-12-27: 2032; 2033-01-03: 2033; 2033-12-26: 2033; 2034-01-02: 2034; 2034-12-25: 2034; 2035-01-01: 2035; 2035-12-31: 2035
|  | Color Keys: | Coursework | Research | Work | Teaching | Milestones | Outside Work
Task ID | Task Name | Category | Duration (weeks) | Preceding Tasks | Custom Start Date | Start Date | End Date | Hello | Task Done | time axis 2024-08-26 to 2035-12-31
1 | Course 1 | Coursework | 12 |  |  | 2024-08-26 | 2024-11-11 | Coursework | Not Done | bar: 2024-08-26 to 2024-11-11
2 | Course 2 | Coursework | 12 | 1 |  | 2024-11-18 | 2025-02-03 | Research | Not Done | bar: 2024-11-18 to 2025-02-03
3 | Prototype build | Milestones | 4 | 2 |  | 2025-02-10 | 2025-03-03 | Work | Not Done | bar: 2025-02-10 to 2025-03-03
4 | Proposal defense prep | Work | 2 | 3 |  | 2025-03-10 | 2025-03-17 | Teaching | Not Done | bar: 2025-03-10 to 2025-03-17
5 | Defense prep | Teaching | 3 | 2 |  | 2025-02-10 | 2025-02-24 | Milestones | Not Done | bar: 2025-02-10 to 2025-02-24
6 | Begin Year 2 | Milestones | 2 |  | 2025-08-27 | 2025-08-25 | 2025-09-01 |  | Not Done | bar: 2025-08-25 to 2025-09-01
7 | Begin Year 3 | Milestones | 1 |  | 2026-08-27 | 2026-08-24 | 2026-08-24 |  | Not Done | bar: 2026-08-24
8 | Begin Year 4 | Work | 1 |  | 2027-08-28 | 2027-08-23 | 2027-08-23 |  | Not Done | bar: 2027-08-23
9 | Project year 2 | Teaching | 6 | 6 |  | 2025-09-08 | 2025-10-13 |  | Not Done | bar: 2025-09-08 to 2025-10-13
10 | Project year 3 | Work | 7 | 7 |  | 2026-08-31 | 2026-10-12 |  | Not Done | bar: 2026-08-31 to 2026-10-12
11 | project year 4 | Teaching | 8 | 8 |  | 2027-08-30 | 2027-10-18 |  | Not Done | bar: 2027-08-30 to 2027-10-18
12 | project year 2 pt 2 | Teaching | 9 | 9 |  | 2025-10-20 | 2025-12-15 |  | Not Done | bar: 2025-10-20 to 2025-12-15
13 | Project 3 | Coursework | 12 |  | 2025-08-21 | 2025-08-18 | 2025-11-03 |  | Not Done | bar: 2025-08-18 to 2025-11-03
Last formatted cells. Extend formatting if you need more tasks.

## Custom Year View
Task ID | Task Name | Category | Duration (weeks) | Preceding Tasks | Custom Start Date | Start Date | End Date |  | Task Done | time axis 2025-08-25 to 2026-08-24
Custom Year Chart (View Only)
Insert the start date for the chart you want to view. This sheet is for viewing purposes only. Do not add any tasks or content here. To add or modify your tasks, do so in the main list in the Full Program sheet.
|  | Year Start Date: | 2025-08-26 | [6 empty] | 2025-08-25: 2025; 2025-12-29: 2025; 2026-01-05: 2026; 2026-08-24: 2026
|  | Year End Date: | 2026-08-23
Task ID | Task Name | Category | Duration (weeks) | Preceding Tasks | Custom Start Date | Start Date | End Date |  | Task Done | time axis 2025-08-25 to 2026-08-24
6 | Begin Year 2 | Milestones | 2 | 0 | 2025-08-27 | 2025-08-25 | 2025-09-01 | 0 | Not Done | bar: 2025-08-25 to 2025-09-01
9 | Project year 2 | Teaching | 6 | 6 |  | 2025-09-08 | 2025-10-13 | 0 | Not Done | bar: 2025-09-08 to 2025-10-13
12 | project year 2 pt 2 | Teaching | 9 | 9 |  | 2025-10-20 | 2025-12-15 | 0 | Not Done | bar: 2025-10-20 to 2025-12-15
13 | Project 3 | Coursework | 12 | 0 | 2025-08-21 | 2025-08-18 | 2025-11-03 | 0 | Not Done | bar: 2025-08-25 to 2025-11-03

## Year 1 Chart
Task ID | Task Name | Category | Duration (weeks) | Preceding Tasks | Custom Start Date | Start Date | End Date |  | Task Done | time axis 2024-08-26 to 2025-08-25
Year 1 Chart (View Only)
This sheet is for viewing purposes only. Do not add any tasks or content here. To add or modify your tasks, do so in the main list in the Full Program sheet.
|  | Year Start Date: | 2024-08-26 | [6 empty] | 2024-08-26: 2024; 2024-12-30: 2024; 2025-01-06: 2025; 2025-08-25: 2025
|  | Year End Date: | 2025-08-24
Task ID | Task Name | Category | Duration (weeks) | Preceding Tasks | Custom Start Date | Start Date | End Date |  | Task Done | time axis 2024-08-26 to 2025-08-25
1 | Course 1 | Coursework | 12 | 0 |  | 2024-08-26 | 2024-11-11 | Coursework | Not Done | bar: 2024-08-26 to 2024-11-11
2 | Course 2 | Coursework | 12 | 1 |  | 2024-11-18 | 2025-02-03 | Research | Not Done | bar: 2024-11-18 to 2025-02-03
3 | Prototype build | Milestones | 4 | 2 |  | 2025-02-10 | 2025-03-03 | Work | Not Done | bar: 2025-02-10 to 2025-03-03
4 | Proposal defense prep | Work | 2 | 3 |  | 2025-03-10 | 2025-03-17 | Teaching | Not Done | bar: 2025-03-10 to 2025-03-17
5 | Defense prep | Teaching | 3 | 2 |  | 2025-02-10 | 2025-02-24 | Milestones | Not Done | bar: 2025-02-10 to 2025-02-24
13 | Project 3 | Coursework | 12 | 0 | 2025-08-21 | 2025-08-18 | 2025-11-03 | 0 | Not Done | bar: 2025-08-18 to 2025-08-25

## Year 2 Chart
Task ID | Task Name | Category | Duration (weeks) | Preceding Tasks | Custom Start Date | Start Date | End Date |  | Task Done | time axis 2025-08-25 to 2026-08-24
Year 2 Chart (View Only)
This sheet is for viewing purposes only. Do not add any tasks or content here. To add or modify your tasks, do so in the main list in the Full Program sheet.
|  | Year Start Date: | 2025-08-25 | [6 empty] | 2025-08-25: 2025; 2025-12-29: 2025; 2026-01-05: 2026; 2026-08-24: 2026
|  | Year End Date: | 2026-08-23
Task ID | Task Name | Category | Duration (weeks) | Preceding Tasks | Custom Start Date | Start Date | End Date |  | Task Done | time axis 2025-08-25 to 2026-08-24
6 | Begin Year 2 | Milestones | 2 | 0 | 2025-08-27 | 2025-08-25 | 2025-09-01 | 0 | Not Done | bar: 2025-08-25 to 2025-09-01
9 | Project year 2 | Teaching | 6 | 6 |  | 2025-09-08 | 2025-10-13 | 0 | Not Done | bar: 2025-09-08 to 2025-10-13
12 | project year 2 pt 2 | Teaching | 9 | 9 |  | 2025-10-20 | 2025-12-15 | 0 | Not Done | bar: 2025-10-20 to 2025-12-15
13 | Project 3 | Coursework | 12 | 0 | 2025-08-21 | 2025-08-18 | 2025-11-03 | 0 | Not Done | bar: 2025-08-25 to 2025-11-03

## Year 3 Chart
Task ID | Task Name | Category | Duration (weeks) | Preceding Tasks | Custom Start Date | Start Date | End Date |  | Task Done | time axis 2026-08-24 to 2027-08-23
Year 3 Chart (View Only)
This sheet is for viewing purposes only. Do not add any tasks or content here. To add or modify your tasks, do so in the main list in the Full Program sheet.
|  | Year Start Date: | 2026-08-24 | [6 empty] | 2026-08-24: 2026; 2026-12-28: 2026; 2027-01-04: 2027; 2027-08-23: 2027
|  | Year End Date: | 2027-08-22
Task ID | Task Name | Category | Duration (weeks) | Preceding Tasks | Custom Start Date | Start Date | End Date |  | Task Done | time axis 2026-08-24 to 2027-08-23
7 | Begin Year 3 | Milestones | 1 | 0 | 2026-08-27 | 2026-08-24 | 2026-08-24 | 0 | Not Done | bar: 2026-08-24
10 | Project year 3 | Work | 7 | 7 |  | 2026-08-31 | 2026-10-12 | 0 | Not Done | bar: 2026-08-31 to 2026-10-12

## Year 4 Chart
Task ID | Task Name | Category | Duration (weeks) | Preceding Tasks | Custom Start Date | Start Date | End Date |  | Task Done | time axis 2027-08-23 to 2028-08-21
Year 4 Chart (View Only)
This sheet is for viewing purposes only. Do not add any tasks or content here. To add or modify your tasks, do so in the main list in the Full Program sheet.
|  | Year Start Date: | 2027-08-23 | [6 empty] | 2027-08-23: 2027; 2027-12-27: 2027; 2028-01-03: 2028; 2028-08-21: 2028
|  | Year End Date: | 2028-08-20
Task ID | Task Name | Category | Duration (weeks) | Preceding Tasks | Custom Start Date | Start Date | End Date |  | Task Done | time axis 2027-08-23 to 2028-08-21
8 | Begin Year 4 | Work | 1 | 0 | 2027-08-28 | 2027-08-23 | 2027-08-23 | 0 | Not Done | bar: 2027-08-23
11 | project year 4 | Teaching | 8 | 8 |  | 2027-08-30 | 2027-10-18 | 0 | Not Done | bar: 2027-08-30 to 2027-10-18